## Scope to be Delivered
|  |  |  | (-)W1 | (-W2) | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18
| Assign | Start | Date | 2018-06-11 | 2018-06-18 | 2018-06-25 | 2018-07-02 | 2018-07-09 | 2018-07-16 | 2018-07-23 | 2018-07-30 | 2018-08-06 | 2018-08-13 | 2018-08-20 | 2018-08-27 | 2018-09-03 | 2018-09-10 | 2018-09-17 | 2018-09-24 | 2018-10-01 | 2018-10-08 | 2018-10-15 | 2018-10-22
a.Course Content will appear with visually appealing format which will be mutually decided in Week 1 of Engagement |  | 2018-06-11 | 2018-06-18 | bar: (-)W1 to (-W2)
Prepare required animation | Srikant | 2018-06-11 | 2018-06-18 | bar: (-W2)
Intuitive presentation and provoking attention and thought | Srikant | 2018-06-11 | 2018-06-18 | bar: (-W2)
b.Course Content can contain Text, Video, Audio and can appear in English & Hindi languages |  | 2018-06-11 | 2018-06-25 | bar: (-)W1 to W1
2nd language conversion | Bikram | 2018-06-18 | 2018-07-02 | bar: W1
2nd language display | Bikram | 2018-06-18 | 2018-07-02 | bar: W1
Audio Narration | Bikram | 2018-06-18 | 2018-07-02 | bar: W1
c.Course Assignment - A particular Course can be assigned to a particular Resource/Group. |  | 2018-06-11 | 2018-06-25 | bar: (-)W1 to W1
Access control based on group privileges | Ashish | 2018-06-11 | 2018-06-25 | bar: W1
Access control based on individual privileges , progress level | Ashish | 2018-06-11 | 2018-06-25 | bar: W1
Upload privileges would only be enabled for individuals who have been granted permission , to be automatically revoked after 1 day or duration as applicable | Ashish | 2018-06-11 | 2018-06-25 | bar: W1
d.Restriction can be imposed for completion of Course, sequencing of Course
Course access rules - e.g advanced course shouldn't be provisioned before the beginner level is completed . In simple terms graded enablement of courses | Ashish | 2018-06-18 | 2018-07-02 | bar: (-W2) to W2
e.g daywise progressive enablement of courses e.g day-2 portion should be enabled only after day-1 is done | Ashish | 2018-06-18 | 2018-07-02 | bar: W2
e.Pre-Quiz and Layman Insight – Progressively prepare someone who has no or limited foundation knowledge in this area
3-4 beginner alignment type of courses for those who cannot complete Pre-Quiz and layman insight | Ashish | 2018-06-18 | 2018-07-02 | bar: (-W2) to W2
Beginner alignment course from vedata | Vedanta
f.It will have facility of Quiz at the end of each lessons/topics (multiple choice, fill in the blanks, …).
Quiz at the end of each lesson / topic various formats | Ashish | 2018-06-18 | 2018-07-02 | bar: (-W2) to W2
Multiple choice | Ashish | 2018-06-18 | 2018-07-02 | bar: W2
Fill in th blanks | Ashish | 2018-06-18 | 2018-07-02 | bar: W2
g.Admin. can select group of questions randomly for each individual
8-10 batteries of questions . Each battery consists of 40 questions . No of batteries and max questions to be configurable | Ashish | 2018-06-25 | 2018-07-02
h.There should be facility to add Reading Comprehension/Case Study type of questions floated by SMEs where each of answers will display the consequences to the individual in ‘Results Display’
Build frame work solution for this case | Tanay | 2018-06-18 | 2018-07-16 | bar: (-W2) to W4
Test with 5-6 different type of scenarios | Tanay | 2018-06-18 | 2018-07-16 | bar: W4
i.SMEs can be able to create ‘Forums’ to discuss a particular topic. Summary of the discussed topic will be mailed to SMEs (also appear in their Dashboard) to create ‘Knowledge Base’ and enrich the Course Content
SME would have provision to create forum | Tanay | 2018-06-18 | 2018-07-02 | bar: (-W2) to W2
Forum would be of 3 types ► Forum to share information blogs , research paper ► Forum to answer questions in a simplified manner ► Forum to create questions relevant to context ○ For the Create Questions forum the contributor has to submit questions in a specific xls template | Tanay | 2018-06-18 | 2018-07-02
Quiz mode restrictions
Limit opening of browser instance while quiz in progress | Tanay | 2018-06-25 | 2018-07-09 | bar: W1 to W3
Exit Quiz to be only enabled at Training centre | Tanay | 2018-06-25 | 2018-07-09
j.Users will have the Dashboard showing the Courses & Results, Wish List of Courses, Forums they subscribed & Summarized Discussions
User dashboards to indicate courses and their results | Srikant | 2018-06-11 | 2018-06-25 | bar: (-)W1 to W1
Strength in specific areas in scale of x/10 | Srikant | 2018-06-18 | 2018-06-25 | bar: (-W2) to W1
Wish List of courses | Srikant | 2018-06-11 | 2018-06-18 | bar: (-)W1 to W1
Participation score in discussions | Srikant | 2018-06-18 | 2018-06-25 | bar: (-W2) to W1
k.There will be Management Dashboard showing ‘Courses Calendar’, ‘Performance of Batches’, ‘Status of participation from SMEs’, ‘Feedbacks’ and Focus in particular for specific subjects
Course completion as per timeline | Tanay | 2018-06-18 | 2018-07-09 | bar: (-W2) to W3
Mean score of candidates | Tanay | 2018-06-18 | 2018-07-09 | bar: W3
How many above median , at median , below median | Tanay | 2018-06-18 | 2018-07-09 | bar: W3
Participation in associated activities e.g camarderie ( how much he/she is helping co-workers , colleagues in the training activities) | Tanay | 2018-06-18 | 2018-07-09 | bar: W3
Contribution of material towards simplification process | Tanay | 2018-06-18 | 2018-07-09 | bar: W3
l.Reward for contributors
SME contribution | Tanay | 2018-07-09 | 2018-07-25 | bar: W3 to W5
Trainee contribution | Tanay | 2018-07-09 | 2018-07-25 | bar: W5
a.Platform will be accessible to Vedanta Employees only through existing site of L&D and from Desktops, Laptops, Andriod & iOS Phones with minimal variations.
Corporate SSO login and access | Tanay | 2018-07-02 | 2018-08-06 | bar: W2 to W7
Exit quiz to be enabled only at training centre desktops | Tanay | 2018-07-16 | 2018-08-06 | bar: W4 to W7
In Quiz mode no browsers would open or other window would open except notepad | Tanay | 2018-07-16 | 2018-08-06 | bar: W4 to W7
Android App Integration ( App already exists , we just have to integrate) |  | 2018-07-16 | 2013-08-06
IoS App Integration ( App already exists , we just have to integrate) |  | 2018-07-16 | 2013-08-13
b.Platform will be installed in L&D Server and Desktops (locally) at Potline Control Rooms. It will be sync with the Server daily with batch job (offline mode)
L&D platform to be hosted in central data centre accessible to L&D and other centres over internet | Srikant | 2018-06-25 | 2018-07-02 | bar: W1 to W2
To be available also n pot room in offline mode as internet access is not possible due to EM effect | Srikant | 2018-06-25 | 2018-07-02 | bar: W1 to W2
Daily synch to be materialized through MySql DB dump | Srikant | 2018-06-25 | 2018-07-02 | bar: W1 to W2
c.Automation workflow to upload content and list of questions
Excel file earmarked regions for following upload types | Srikant | 2018-07-02 | 2018-08-06 | bar: W2 to W7
Information Content only | Srikant | 2018-07-02 | 2018-08-06 | bar: W7
What , How , Why , When | Srikant | 2018-07-02 | 2018-08-06 | bar: W7
Trigger, Event,Consequence,Response, Action cycle for each process | Srikant | 2018-07-02 | 2018-08-06 | bar: W7
Videos which would completely demonstrate the process | Srikant | 2018-07-02 | 2018-08-06 | bar: W7
Each user should have a unique profile
All activities to be linked to the profile | Asish | 2018-06-11 | 2018-06-25 | bar: (-)W1 to W1
All roles and privileges to be linked to profile | Asish | 2018-06-11 | 2018-06-25 | bar: (-)W1 to W1
User can raise questions in the following context
Giving reference of a page | Chandra | 2018-07-16 | 2018-08-06 | bar: W4 to W7
Giving reference of a certain word | Chandra | 2018-07-16 | 2018-08-06 | bar: W4 to W7
Giving reference of a certain line | Chandra | 2018-07-16 | 2018-08-06 | bar: W4 to W7
Preview view of to be uploaded and posted
Preview view for admin and SME | Chandra | 2018-07-25 | 2018-08-13 | bar: W5 to W8
Provision to commit or reject | Chandra | 2018-07-25 | 2018-08-13 | bar: W5 to W8
Contributor Dashboard
Any additional plugin to be installed
Mobi-Site kind of stuff (accessible in all devices??)
Dev closure of LIR
User Acceptance
Final deployment
Operate and Improve
Signing of support clause
Start of Project
Vedanta to onboard required SMEs to provide desired material for LIR and review of content and structure and share feedback
Vedanta to connect BJS with its IT department for deployment and other SSO related activities

## Plugins
Already Installed
To be Installed
May be Installed if bringing additional features
1 | LearnPress – Course Review | LearnPress Course Review - An extension plugin for LearnPress.
| LearnPress – Prerequisites Courses | LearnPress Prerequisites is an add-on for LearnPress allow you to set prerequisite courses for a certain course in a LearnPress site.
| LearnPress – Course Wishlist | LearnPress Wishlist add wishlist feature to your LearnPress course in your site.
| LearnPress Export Import – WordPress extension for LearnPress | LearnPress Export/Import bring you feature to export course, lesson, quiz, question from a LearnPress site to back up or bring to another LearnPress site.
| WPComplete | WPComplete is a WordPress plugin that helps your students keep track of their progress through your course or membership site
| Wptouch | Make your WordPress website mobile-friendly with just a few clicks.
| Emoji Settings | Emoji Settings adds an option within your Writing Settings page to disable or enable emojis.
| Video Lessons Manager | Easily manage your video courses, webinars, and content for your WordPress users to watch, track, comment and follow. The Video Courses Manager plugin lets users track and organize online video courses and webinars on your WordPress site. The Video Lessons Manager plugin allows you to manage video courses, lectures and lessons while users and administrators can track progress, leave comments and mark favorites. You can set up online video-driven courses by creating learning units supported by course content. The Video Courses Manager plugin allows you to manage video courses, video tutorials and lessons while users and administrators can track progress, leave comments and mark favorites. This plugin creates a WordPress learning management system where uses can check course progress, and video content. The pro version of the plugin also supports adding pay-per-view lessons for limited time periods while using direct payment option and checkout with PayPal, Stripe and more or Micropayment solution. The pro plugin supports watching videos generated on Vimeo Private Video Channels or Wistia. Build several courses or lessons based on your Vimeo or Wistia account. Display your videos in any page or post on your WordPress site.
Version Info
| LearnPress – Fill in Blank Question | Fill in Blank question type for LearnPress WordPress LMS Plugin
| Analytics Head | This plugin adds tracking code for Google Analytics to your WordPress <head> section, so you can authorize your site in Google Webmaster Tools.
| Coming Soon Viral Page by Growtheme | Coming Soon Viral Page by Growtheme is the only plugin that helps you building your blog audience from scratch, even if you have not published any post on your own Blog yet.
| Users by Date Registered | Allows you to filter your users by date registered.
| Login by Auth0 | This plugin gives WordPress a new Login Widget (powered by Auth0) that enables: Universal authentication +30 Social Providers Enterprise connections (ADFS, Active directory / LDAP, SAML, Office 365, Google Apps and more) Connect your own database Passwordless connections (using SMS, Magic links and Email codes) Ultra secure Multifactor authentication Password policies Email validation Mitigate brute force attacks Easy access to your users data User stats Profile data Login history and locations
| Accredible Certificates & Open Badges | Certificates, open badges and blockchain credentials. Create, update and manage them on your Wordpress site.
| WP Post Email Notification | A plugin sending email notifications to subscribers when a new post is published.
| Easy Student Results | Result Management System for School, College and University. Use [esr_results] to display result and [esr_students] to display student list.
| Landing Page Builder – Free Landing Page Templates | Create Landing Pages & Custom Pages using pre designed Free Landing Page templates with Ultimate
| Visual Sitemap | Display an interactive visual sitemap of pages, tags, and categories in admin.
| Chained Quiz | This is an unique chained / conditional logic quiz plugin that lets you create quizzes where the next question depends on the answer to the previous question.Features Create unlimited number of quizzes and questions This free quiz plugin is fully functional: there is no limitation to the number of quizzes, questions or results you can have. Questions support: single-choice, multiple-choice, open-end (essay) The quiz will generate respectively a group of radio buttons, checkboxes, or a text area. Even open-end (essay) questions can have possible answers that will be evaluated for match with the user’s answer. Assign points to each answer This is optional. The points will be summarized at the end to calculate final result. Calculate result based on the points (unlimited number of results and from/to points) Depending on how many points the user has collected you can assign a result and display different content at the end of the quiz. The result can be used to give user recommendation, to direct them to another page, to offer them something to sell and so on. Define what to do when specific answer is chosen This is where the real magic of the chained quiz happens. You can define to go to next question in the quiz, go to a specific selected question, or finish the quiz. Export user’s answers to a CSV file – with or without details The CSV file can be used to analyze user results in Excel, import it in a database and so on. Go PRO with WatuPRO The quizzes created with this plugin can be transferred to the most powerful WordPress tests suite WatuPRO where you can support chained logic via this free addon. This unique quiz plugin lets you guide the user through the questions in the way you want. It’s not only a very powerful tool for creating exams and quizzes, but can be used also to funnel a sales process depending on user’s selection. Developers API We are just starting to add hooks, so stay tuned for detailed documentation. For now the main available hook is: – “chained_quiz_completed” – sends the completion ID as argument to the call. Getting Started Once activated the plugin go to Chained Quiz -> Quizzes in your WP dashboard and create your first quiz. After entering the quiz title, description and other settings you will be redirected to create the quiz results / outcomes. They define what happens after the user completes the quiz, depending on the points they collected from the different answers. Creating results is optional but very powerful because you can present completely different content to the user depending on what path they took through the quiz and how many points were assigned to their answers. You can use the result description box for this result-dependent content or even redirect to another page. After you create your results you will be redirected to creating the actual questions in the quiz. The answer to each question has an action which defines what happens if the user selects it: they can go to the next question, to a specific selected question (this is where the chaining magic happens), or to finalize the quiz. Don’t forget that the conditional logic quiz must be published before it becomes accessible. Publishing happens when you manually place the shortcode of the quiz in a post or page or select the option “Automatically publish” when you save it. *** Attention Multi-Site (WP Network) Users! *** The plugin is perfectly compatible with multi-site installations but it should be activated as blog admin and NOT as superadmin.
| Psychological tests & quizzes | Create psychological tests/quizzes with scales connected to results through simple formulas like "extraversion > 50%"
| Interactive Content – H5P | Create and add rich content to your website for free. Some examples of what you get with H5P are Interactive Video, Quizzes, Collage and Timeline.
| Watu Quiz | Creates exams and quizzes with unlimited number of questions and answers. Assigns grade after the quiz is taken. Mobile / touch - friendly.
| Discussion Board – WordPress Forum Plugin | Discussion Board is an easy way to add a forum to your WordPress site.
| Photo Gallery by WD – Responsive Photo Gallery | Photo Gallery is a powerful gallery plugin with a list of advanced options for creating stunning image galleries. Add the responsive plugin with cool
| Private groups | For bbPress - Creates private forum groups
| WP-Forum Latest Posts | WP-Forum Latest Posts surprisingly lists the latest posts from your WP-Forum. There are some option to customize the output and others.
| ResponsiveVoice Text To Speech | ResponsiveVoice is a HTML5-based Text-To-Speech library designed to add voice features to WordPress across all smartphone, tablet and desktop devices. It supports 51 languages through 168 voices and has no dependencies. Languages include UK English, US English, Spanish, French, Deutsch, Italian, Greek, Hungarian, Turkish, Russian, Dutch, Swedish, Norwegian, Japanese, Korean, Chinese, Hindi, Serbian, Croatian, Bosnian, Romanian, Catalan, Australian, Finnish, Afrikaans, Albanian, Arabic, Armenian, Czech, Danish, Esperanto, Hatian Creole, Icelandic, Indonesian, Latin, Latvian, Macedonian, Moldavian, Montenegrin, Polish, Brazilian Portuguese, Portuguese, Serbo-Croatian, Slovak, Spanish Latin American, Swahili, Tamil, Thai, Vietnamese and Welsh. | Hindi & tamil language can be configured
| Users Insights | Premium plugin: The Users Insights plugin puts your WordPress users data in one intuitive, beautiful and searchable place, ready for you and your team to interact with.
| Users Role Editor | Premium plugin: With User Role Editor WordPress plugin you can change user role (except Administrator) capabilities easy, with a few clicks. Just turn on check boxes of capabilities you wish to add to the selected role and click “Update” button to save your changes. That’s done. Add new roles and customize its capabilities according to your needs, from scratch of as a copy of other existing role. Unnecessary self-made role can be deleted if there are no users whom such role is assigned. Role assigned every new created user by default may be changed too. Capabilities could be assigned on per user basis. Multiple roles could be assigned to user simultaneously. You can add new capabilities and remove unnecessary capabilities which could be left from uninstalled plugins. Multi-site support is provided.
Note on C24: Windows User: This plugin gives WordPress a new Login Widget (powered by Auth0) that enables: Universal authentication +30 Social Providers Enterprise connections (ADFS, Active directory / LDAP, SAML, Office 365, Google Apps and more) Connect your own database Passwordless connections (using SMS, Magic links and Email codes) Ultra secure Multifactor authentication Password policies Email validation Mitigate brute force attacks Easy access to your users data User stats Profile data Login history and locations Technical Notes IMPORTANT: By using this plugin you are delegating the site authentication to Auth0. That means that you won’t be using the WordPress database to authenticate users anymore and the default WP login box won’t show anymore. However, we can still associate your existing users by merging them by email. This section explains how. When you install this plugin you have at least one existing user in the database (the admin user). If the site is already being used, you probably have more than just the admin. We want you to keep those users, of course. Migrating Existing Users Auth0 allows multiple authentication providers. You can have social providers like Facebook, Twitter, Google+, etc., you can have a database of users/passwords (just like WordPress but hosted in Auth0) or you can use an Enterprise directory like Active Directory, LDAP, Office365, SAML and others. All those authentication providers might give you an email and a flag indicating whether the email was verified or not. We use that email (only if its verified) to associate a previous existing user with the one coming from Auth0. If the email was not verified and there is an account with that email in WordPress, the user will be presented with a page saying that the email was not verified and a link to “Re-send the verification email”. For both scenarios you may configure in the WP admin whether is mandatory that the user has a verified email or not. Accessing Profile Information WordPress defines a function called wp_get_current_user to populate the global variable current_user with the logged in WP_User. Similarly we define get_currentauth0userinfo that populates current_user and currentauth0_user with the information of the Normalized profile Enabling dual (Auth0 and WordPress) login You can enable the standard WordPress login by turning on the “WordPress login enabled” setting (enabled by default). This will make visible a link on the login page to swap between both. Using the plugin widget You can enable the Auth0 as a WordPress widget in order to show it in the sidebar. The widget inherits the plugin settings and it can be overridden with its own settings. Also, a new layout setting is enabled in order to be shown as a modal. Enabling the “Show as modal” setting, a button which trigger the modal is generated. Using the login widget as a shortcode Also, you can use the Auth0 widget as a shortcode in your editor. Just add the following: [auth0] It can be customized by adding the following attributes: form_title: string dict: string, should be a the language or a valid json with the translation (see https://github.com/auth0/lock/wiki/Auth0Lock-customization#dict-stringobject) social_big_buttons: boolean gravatar: boolean username_style: string, “email” or “username” icon_url: string (valid url) extra_conf: string, valid json show_as_modal: boolean modal_trigger_name: string, button text Example: [auth0 show_as_modal="true" social_big_buttons="true" modal_trigger_name="Login button: This text is configurable!"] All the details about the parameters on the lock wiki (https://github.com/auth0/lock/wiki/Auth0Lock-customization)
Note on C28: Windows User: Google Analytics Dashboard Google Analytics Dashboard for WordPress – by Analytify makes Google Analytics simple for everywhere in WordPress (posts, pages and custom post types). It presents the statistics from Google Analytics in a beautiful way under the WordPress Posts/Pages at front end, backend and in its own Dashboard. Now you can get Google Analytics Dashboard inside your WordPress Dashboard within a minute. Top Features of this Google Analytics plugin: Super easy installation. 1-Click Authentication process and It adds Google analytics tracking code to your website. No need to copy any code manually. Enhanced ecommerce Google analytics Tracking Add-ons for WooCommerce & Easy Digital Downloads are available (Premium) Google Analytics Stats (General) under the single posts/pages as a block in wp-admin List of top Countries List of top Cities SOCIAL MEDIA Statistics List of top Referrers Browsers List of top Referrers Mobile device Statistics See What’s happening when users come to your site (Bounce rate of top pages) REAL-TIME Statistics of your site in dashboard.(Premium) Campaigns Statistics (Premium) ShortCodes (Simple and Advanced) for Custom Statistics of your own choice (Premium) Use ShortCodes in Widgets (Premium) Helps in SEO optimization and allows you to see traffic data for individual blog posts and pages. It can be easy customizable with CSS, you can give it any shape you want. You can extend it to at any level. Usage of API’s are very easy to work with. Google Analytics Stats (Full) under the single posts,pages & Custom Post Types as a block in wp-admin (Premium) Google Analytics Stats (Full) under the single posts,pages & Custom Post Types as a block at front-end (Premium) General Statistics (Sessions, Users, Bounce rate, Average time on site, Average pages, PAGEVIEWS, NEW/RETURNING Visitors) How people are finding you (TOP KEYWORDS) [New] Dashboard dropdown menu now remembers your last selection of time period. Analytify 2.1 is here! Discover Google Analytics Like Never Before! Must check those stunning Screenshots! Premium Version: This plugin has a premium version, which is more easy to install, and shows Real-Time Stats, Campaign Stats, ShortCodes, Front-end Stats and more reports in backend and front-end. Also premium version has better e-commerce tracking (Buy Add-ons with premium), and campaigns management. Get the affordable Premium Version from analytify.io . Bundle price is also available with Addons. Google Analytics Premium Partner – Read what Google is saying about us. WooCommerce Enhanced eCommerce tracking and report dashboard right inside your WordPress is now available. Take a look. Google Analytics by Analytify Development on Github This Google analytics plugin is also available on github and ready to take bugs and pull requests. For Support, you can buy the PRO version, this will give access to premium updates, support and features. Following are the important add-ons which empower you to setup Google Analytics like a boss. It really helps your clients, online stores, etc. Google Analytics Goals Dashboard[NEW Launched] Google Analytics eCommerce Tracking for WooCommerce Google Analytics eCommerce Tracking for Easy Digital Downloads Automated Email Notifications Google Analytics Campaigns Tracking [Free]Google Analytics Dashboard Widget Following is a Complete Hierarchy Structure of Analytify Products Suite. Analytify Core (Free and Required for all add-ons) *Dashboard widget (Free) Analytify Pro (Paid) Campaign Tracking (Paid) Email Notifications (Paid) Google Analytics Goals Tracking and Dashboard (Paid) Enahnced E-commerce Google Analytics Tracking for WooCommerce (Paid) Enahnced E-commerce Google Analytics Tracking for Easy Digital Downloads (Paid) 100% Multilingual & Translateable WPML Compatible Available in Following languages: * German 97% * Russian 56% * Norwegian 75% * Spanish 50% * Dutch 96% Notes Analytify is the best Google Analytics plugin for WordPress. We make Google Analytics look EASY. You know all about Google Analytics and love the data it provides, but wouldn’t it be nice if there is a tool to make managing all of that complex information simpler? You’re in luck. Google Analytics Was Never This Fun In WordPress before. Following is a list of Testimonials you must read them once. Testimonial # 1 Great way to understand your audience I’ve been using the Pro version for quite a while. I really love how it gives me in-depth information about each individual post. That kind of info is hard to navigate to in Google Analytics even if you’re relatively familiar with it already. I discovered all kinds of new things about how people land on my site and how they engage with it just by activating the plugin and looking at the information it provides in the Dashboard and on individual posts. The author is also an official Google analytics Partner, which I think speaks volumes. Well done all around, highly recommended! Testimonial # 2 Best Google Analytics Plugin This is something that clients really love as they of course want to see traffic to their site. However many do not want to log into google analytics and work their way through its rather complicated reporting modules. This gives all the headline stuff and more. What’s really neat is that it does it for every single page as well. So you can really see what’s going on for a particular post. So a google search for X led to this page. It also has great realtime reporting for the paid version. I had one small issue and the developer responded and addressed it immediately. Very impressed. It’s become a default plugin. Testimonial # 3 Excellent Integrations with Google Analytics Many of my clients don’t want to view analytics outside their dashboard. This plugin integrates GA beautifully within the WordPress admin panel. I suggest you give it a spin. The developers are also very nice and dedicated to the plugin, which goes a long way. Testimonial # 4 Outstanding support and product Besides thinking the plugin is wonderful, I am equally impressed with the support team. I had issues and they emailed back and forth to resolve my issues and even update the plugin for me. I highly recommend this plugin which has been very beneficial to my analytics, but just as important, I appreciate the support in resolving my issue in a very timely manner. You may buy the premium version to support the development. http://analytify.io/details
Note on C33: Windows User: Landing page Plugin lets you create beautiful and high converting landing pages in mere minutes without writing a single line of code. With our Landing Page templates your landing page will perform out of the box and increase your conversion rates instantly. Switch templates to test which template converts better, without any technical knowledge. Upgrade to the Advanced version Built in Beautiful MailChimp subscribe forms lets you increase your subscribers on the go without any technical assistance. Landing page plugin is complete plugin ready to work out of the box with just one click Install you will be creating landing page without writing a single line of code or technical assistance. Use the integrated SEO meta box to completely optimize your post title, meta keywords and meta description to increase your search engine rankings. Our specifically designed templates Boost your sales and conversions instantly. Landing Page Templates : With our collection of landing page templates your landing pages will look as good as they perform. Designed to maximize your conversions. Our landing page templates offers complete flexibility and are easily customizable. Forms : With Landing Page plugin you can integrate any WordPress Form Plugin (including : Gravity Forms, Contact Form 7 , Ninja Forms and many more.). Or you can add custom form shortcodes + HTML forms. MailChimp Forms : Landing Page Plugin Integrate Beautiful MailChimp Forms for your marketing and maximize your conversions instantly. Capture leads on your landing page and send them directly to MailChimp. GetResponse Forms : Landing Page Plugin Integrate Beautiful GetResponse Forms for your marketing and maximize your conversions instantly. Capture leads on your landing page and send them directly to GetResponse. Email Autoresponder : With Landing Page plugin you can create and send Email Autoresponder right from your WordPress Dashboard. Create beautiful HTML emails and send them to your Landing Page Leads right at the moment when they subscribe. Coming Soon Pages : With Landing Page plugin you can create beautiful Coming soon pages easily and publish them immediately, Or set a schedule for publishing. Landing page plugin also includes a coming soon counter. Sales Pages : Landing page Plugin have beautiful and effective sales page templates to improve your sales. Google Fonts : Landing page Plugin supports Google fonts for beautiful typography and to make your landing pages conversion rate better. Set Landing Page as Front Page/Home Page : Set Landing page as home page or front page to target all the traffic on your site.Capture your leads and sales from front page. Custom CSS/JS : If you are a developer or designer and want to tweak design or enhance usability, then there is no need to mess with Landing Page plugin files because Landing Page plugin offers Custom CSS/JS (JavaScript) feature and customize whatever you want. Landing Pages Create landing pages easily in minutes. Creating landing pages has never been this easy. With this plugin you will save a lot of time. No more copy/pasting the content and manually creating landing pages. Create beautiful Landing Page on your WordPress site, Visual Landing Page Editor to view changes being made on the fly! Landing Page Features : Responsive template. Shortcodes Supported in landing page. Color customizations. Custom CSS & JavaScript. Custom SEO for landing pages. Yoast SEO supported. Pre Designed Templates. Set Landing page as homepage/front page. Add subscribe forms in your landing page. (Using Subscribe Form Plugin ) Add Contact forms in your landing page. (Using Contact Form Builder ) Empty Template for creating your own landing page templates. Integrated 250+ Google fonts. Landing Page Premium Features : All landing page templates unlocked. MailChimp subscribe form integration for Landing page. GetResponse subscribe form integration. Database subscribe form integration. Auto-responder for your leads. Export Database Subscribers in .CSV file. Create Custom templates. Create unlimited landing pages. Set a landing page as homepage. Supports Custom CSS. ShortCode supported custom template. Google Analytics Support. Custom CSS & JavaScript. Advanced Features for developers & Designers. Landing Page plugin gives you all the power to create & design your own landing pages. Use our pre built landing page templates or create your own, Creating Landing Pages was never easier. Now you can easily use your HTML templates for your landing pages, coming soon pages or simple page. Landing pages are an ideal way to convert more of your passive website visitors into active leads or email list subscribers. Landing pages are the bread and butter of any successful marketing campaign. They are choc full of customized content that speaks to your website visitors. Your Landing Page content speaks to your website visitors because it delivers the exact, specific information that your visitor was expecting. Landing pages are aligned with your marketing messages 110%, and always have one clear objective in mind: making your website visitors take a specific course of action. It really is that simple. Online advertising campaigns that use a landing page usually sees a conversion rate increase of at least 25%. And, with some A/B Split testing, this figure can be even higher. The main reason that landing pages convert so well is because you can design, build, and draft compelling copy that specifically matches your advertisement. If you compare a homepage vs. a landing page you can see why landing pages are so important to your marketing’s success. Your homepage is designed with a more general purpose in mind. It speaks to your overall brand and corporate values and is typically loaded with links and navigation to other areas of your site. It’s designed to encourage exploration. This plugin works great with the Subscribe Form makes adding subscribe forms to your website very easy. Search engine optimization of landing pages is really easy with this ‘tool’. Get your marketing campaign up and running with Ultimate Landing Page Pro What are benefits of landing pages ? A: The benefits of Landing Page are : Landing page leads to more qualified leads. More qualified leads lead to more conversion opportunities. More landing pages enhance the SEO of your website increasing the possibilities that your website will be found and visited. You need more sales collateral (or free offers) to present to each type of visitor which creates on site variety enticing visitors to stay on your website longer. Landing page leads are naturally segmented into different types of visitors so you can continue to tailor your ongoing messages to where they are in the buying process and thereby increasing your chances of creating a sale. When Should I Use a Landing Page ? A: You should try to use a landing page for every inbound advertising campaign you operate. You might be selling multiple products or setting up promotional offers for different user segments and your homepage can’t deal with this level of message differentiation is you should use a landing page. Lead generation landing pages The most valuable piece of information you can get from a lead gen page is someone’s email address – which gives you permission to continue talking/marketing to them. Once you have a lead’s permission, you then try to convert them into a customer by combining the two most powerful 1-to-1 communication tools a marketer has – email and landing pages. Click-through landing pages Click-through pages (sometimes called jump pages) are designed as a conduit between a marketing ad and it’s final destination. The goal of a click-through page is to “warm-up” the visitor to the product/service you are trying to sell. Commonly used for e commerce, click-through pages provide enough information to inform the buyer, making them ready to purchase, before pushing them further down the funnel – probably to a shopping cart or checkout.
Note on C66: Windows User: WP Plugin for truly banning users! The BAN Users WordPress Plugin has been developed to enable administrators to quickly BAN (aka disable, suspend…) users from logging into their WordPress user account, as well as the option to change the status of all their posts. For instance setting them to draft to hide them from public viewing. A user can be BANed from the admin users table or via their profile. There are several configurable options that allow the administrator to control how the BAN will be implemented such as redirecting them to a custom holding page, or sending them a custom email notification. Once BANned they will be unable to login until an administrator reinstates their account. Recent Reviews The best plugin I’ve ever used for banning accounts! At last I found plugin that truly bans… OUTSTANDING plugin / support / developer Plugin Features & Options Quickly ban a user for a day, week, month or forever! Send WARNING emails to users, including custom messages. Scramble banned users’ password Change banned users’ role Set spammer status for banned users Disable password reset for banned users Automatically change user’s Posts status (i.e. to pending) when BANned. Table listing banned users, with search feature and quick links Enhanced security to restrict Ban User privilage access Flat icons as alternatives to text based links Modal popup for sending custom messages, with textarea instead of text field Supports Ultimate Member Plugin Force logout when user BANned. Set custom logout URL when BANned. Set message to display when a BANned user attempts to login. If already logged in, display message to user when BANned. Send custom email notification to user when banned/unbanned. Capture unique reason for banning each user. Set duration of BAN using date picker. BANned users highlighted in users table with icon/coloured background row. Users table shows reason user banned. Users table shows date user banned. Users table shows date user reinstated. Support for Accessibility / Screen Readers. Support for BuddyPress Support for CPT (Custom Post Types) Plugin Shortcodes Template values / custom default messages Premium Plugin Features: Buy Premium Version Capture users’ IP/Geodata during login Display IP/Geodata in users table BAN users by date and TIME! Send notifications to specified email addresses when user publishes first post Prevent users with banned email address from registering Prevent users with banned email address from logging in Prevent users with banned ip address from registering Prevent users with banned ip address from logging in Easily manage add/remove/search banned email/ip addresses Include custom CSS/JS in header/footer SPAM prevention Account security – notification for logins when accessed from a new IP How is it Useful? There are multiple reasons why an administrator of a WordPress website may need to block users. One of the most popular reasons is the security of the site. Indeed, most blogs face security issues. Once your site is online and growing in popularity, it can become the target of individuals whose only goal is to destroy your work and to discredit your blog. The BAN Users Plugin enables administrators to deny access to unwanted individuals, and inform those users of the actions taken against them. You want to ban malicious users from logging in. You want to ban users who have breached terms of use or another policy. You want to temporarily control access to admin. You want to restrict a registered user from making any changes during development. You have a client/user who has an unpaid invoice. Ideal solution for moderators who monitor wordpress forums/posts.

## Features in Current Setup
Features enabled in current learnpress | Description
Posts | This feature talks about different types of posts, categorized posts by various authors/contributors
Events | This feature talks about events, categorized events, venues, organizers list
Media | This feature enables uploading of various media like images, video files into the site
Pages | This feature enables the modification of various site pages like blogs, forums,courses, profile pages
Comments | This feature enables the admin to receive all types comments posted by the user after reading through various contents like courses,lessons etc
Contact | This feature talks about the contact forms required by the user to send queries to the websites by submitting their basic details
Forums | This feature enables creation of forums to discuss various topics by contributors/authors/users
Users | This feature handles the user access management by admins. Admin is the super user and they define the different roles to various users. It also allows admins to restrict users to access the specified content of the sites
All-in-one WP migration | This feature enables to import/export/take back up of the entire site as desired
Watu Quizzes | Enables to create various types of quizzes like single choice, multi choice, reading comprehensive(Essay)
Quizzes for learnpress | This connector will allow you to use more powerful third-party quiz plugins for your LearnPress based LM
upload max file size | This feature helps increase Upload Maximum File Size
Wonder Plugin Video Embed | This feature supports YouTube, Vimeo, Wistia, iFrame and self-hosted MP4/WebM videos

## Custom Code
User Dashboard | User can see what are the courses he has covered so far (history 5 years) and scores, no of appearances, requested courses pending for approval, reward points he earned for contributions, forums he is participating, what else
Management Dashboard | What are the Courses running where, no. of Participants, Scores (Avg.) of Groups, Training Calendar, Participation of Contributors, Rewards for Contribution, what else
Contributor Dashboard | Participation in Fourms, Suggestions Summary, Updates to Courses , Reward Points earned, what else
Administrator Dashboard | Workflow for Course Upload, Requests for providing access to particular course, what else
Offline Synchronization
Andrioid & iOS App to reach to the LMS Server to access content